## PHASE-I
Steps # | Phase-I Network Activity Plan
Location : Data Center Activity
Step 1 | Take Backup of existing Switch | HP Aruba | 48 | Non POE | 5
Step 2 | Trace remaining Network uplink cable of core switch
Step 3 | Mount and Install new switch | HP Aruba | 24 | POE | 3
Step 4 | Stack new switchs
Step 5 | Power on new Switch | HP Aruba Core Switch | 24 | Non POE | 2 | 5190
Step 6 | Configure new switch as per old uplink configuration
Step 7 | Connect console and verify device status of all new devices | HP Aruba AP 515 |  |  | 51
Location : B1 Level 1 Access Switch
Step 8 | Mount and Install New switch | 505 |  |  | 11
Step 9 | Power on new Switch in default state
Step 10 | Move All existing uplink and user uplinks from Old switch to New switch | Exeisting
Step 11 | Test & Troubleshoot Network Connectivity
| Location : B1 Level 3 Access Switch | Dlink | 48 |  | 10
Step 12 | Mount and Install New switch
Step 13 | Power on new Switch in default state
Step 14 | Move All existing uplink and user uplinks from Old switch to New switch
Step 15 | Test & Troubleshoot Network Connectivity
Location : B1 Level 5 Access Switch
Step 16 | Mount and Install New switch
Step 17 | Power on new Switch in default state
Step 18 | Move All existing uplink and user uplinks from Old switch to New switch
Step 19 | Test & Troubleshoot Network Connectivity
Location : B1 Level 7 Access Switch
Step 20 | Mount and Install New switch
Step 21 | Power on new Switch in default state
Step 22 | Move All existing uplink and user uplinks from Old switch to New switch
Step 23 | Test & Troubleshoot Network Connectivity
Location : B2 Level 2 Access Switch
Step 24 | Mount and Install New switch
Step 25 | Power on new Switch in default state
Step 26 | Move All existing uplink and user uplinks from Old switch to New switch
Step 27 | Test & Troubleshoot Network Connectivity
Location : B2 Level 4 Access Switch
Step 28 | Mount and Install New switch
Step 29 | Power on new Switch in default state
Step 30 | Move All existing uplink and user uplinks from Old switch to New switch
Step 31 | Test & Troubleshoot Network Connectivity
Location : B2 Level 6 Access Switch
Step 32 | Mount and Install New switch
Step 33 | Power on new Switch in default state
Step 34 | Move All existing uplink and user uplinks from Old switch to New switch
Step 35 | Test & Troubleshoot Network Connectivity

## PHASE-II
Steps # | Phase-II Network Activity Plan
Firewall - Core & Dsitribution switch actvity
Step 1 | Configure firewall Vlan on L3 switch
Step 2 | Configure firewall uplink ports in access mode with FW_VLAN
Step 3 | Configure default route towards firewall for internet connectivity
Step 4 | Configure VLAN as per the VLAN details and IP Schema
Step 5 | Configure VTP Server / VTP Domain on core switch
Step 6 | Confgure VTP Client /VTP Domain on Distribution Switch's
Step 7 | Configure Trunk port on core switch with Native vlan
Step 8 | Configure Trunk port on Distribution switch's with native vlan
Step 9 | Test Distribution switch connectivity on one off the admin machine
Step 10 | Save the configuration on L3 Switch and Distribution switch
Access Switch actvity
Step 11 | Confgure VTP Client /VTP Domain on Cisco L2 Switch's
Step 12 | Configure MGMT vlan on access switch's
Step 13 | Configure Distribution switch port with respective to access layer switch
Step 14 | Test Access switch connectivity on one off the admin machine
Step 15 | Save the configuration on Distribution switch and access switch
DHCP Server - User actvity
Step 16 | Configure windows DHCP helper on Core switch for DHCP server
Step 17 | Configure DHCP pool on DHCP server
Step 18 | Test user connectivity on all floor with respective DHCP relase / Applications / Internet etc
Step 19 | Troubleshooting user conectvity (If required )
End to End Connectivity testing
Step 20 | Check all DHCP Relase/ sever application / Internet
Step 21 | Test & troubleshoot Connectivity of Branch to DC Server
Step 22 | Test & troubleshoot VPN user connectivity over the Internet
Step 23 | Troubleshoot connectivity issue (If required)
Backup of Network Devices
Step 24 | Take Backup of all switch configuration (Core/Distribution/Access)
Step 25 | Sign off Phase-II & Phase-III activity